## Balraj
No | Date | Application | Task | % of completion | Status
1 | 2020-04-29 | RPA Dotnet | [Backend] CRM | 30% | WIP | Following the discussion, we have to decided to have few more tables for the CRM which is in Progress, and also decided to remove four columns at CusteorDetails and also at CustomerRequestData tables based on your suggestion.
Status
WIP
Pending
Completed
Hold

## Vijay
No | Date | Application | Task | % of completion | Status | Comments
1 | 2020-04-30 | MujiStore | MujiStore - Authorization for Stores video | 50% | WIP
Status
WIP
Pending
Completed
Hold

## Bharathi
No | Date | Application | Task | % of completion | Status | Comments
Status
WIP
Pending
Completed
Hold

## Mamatha
No | Date | Application | Task | % of completion | Status | Comments
Status
WIP
Pending
Completed
Hold

## Monisha
No | Date | Application | Task | % of completion | Status | Comments
1 | 2020-04-29 | DotnetAPP | Loginpage (Frontend) | 100% | Completed
Status
WIP
Pending
Completed
Hold

## Sabeena
No | Date | Application | Task | % of completion | Status | Comments
1 | 2020-05-04 | RPA-SALE | PPT Management - Create,view,update,delete | 80% | WIP
2 | 2020-05-05 | RPA-SALE | PPT Management - Create,view,update,delete | 100% | Completed
3 | 2020-05-06 | RPA-SALE | SAMPLE SSRS Report Generation | 80% | WIP
4 | 2020-05-07 | RPA-SALE | SAMPLE SSRS Report Generation | 100% | Completed
5 | 2020-05-08 | RPA-SALE | Report - Export to Excel | 80% | WIP
6 | 2020-05-11 | RPA-SALE | Report - Export to PDF | 80% | WIP
7 | 2020-05-12 | RPA-SALE | Report - Export to CSV | 80% | WIP
8 | 2020-05-13 | RPA-SALE | Report | 90% | WIP
9 | 2020-05-14 | RPA-SALE | Report | 100% | Completed
10 | 2020-05-15 | RPA-SALE | Task - Backend | 100% | Completed
11 | 2020-05-18 | RPA-SALE | Document & notes Sharing | 10% | WIP
12 | 2020-05-19 | RPA-SALE | Document & notes Sharing | 80% | WIP
13 | 2020-05-20 | RPA-SALE | Document & notes Sharing | 100% | Completed
14 | 2020-05-21 | RPA-SALE | RPA-Validations | 20% | WIP
15 | 2020-05-22 | RPA-SALE | RPA-Validations | 80% | WIP
Status
WIP
Pending
Completed
Hold

## Prabu
No | Date | Application | Task | % of completion | Status | Comments
Status
WIP
Pending
Completed
Hold

## Ram
No | Date | Application | Task | % of completion | Status | Comments
Status
WIP
Pending
Completed
Hold

## Rahman
No | Date | Application | Task | % of completion | Status | Comments
Status
WIP
Pending
Completed
Hold

## Mathes
No | Date | Application | Task | % of completion | Status | Comments
Status
WIP
Pending
Completed
Hold